## CS wp
The work packages of contract strategy |  | 1
Work package number | Contracting party label | Tender process | Pricing mechanism | Mngmt/Consultnts fee
1 |  |  |  |  | 1 | FALSE | FALSE | FALSE | 2 | 3 | 4.4 | 2 | 3 | 4.4 | 50 | gmp |  |  |  |  | 0.05 | 0.06 | 0.075
2 |  |  |  |  | 1 | FALSE | FALSE | FALSE | 1 | 4.025 | 4.15 | 4.325 | 6 | 10 | 15 | 50 | 50 | 9.35 | 50 | 50 | 0.1 | 0.125 | 0.15
3 | [5 empty] | FALSE | FALSE | FALSE | 3 | 0.64 | 0.65 | 0.665 | 0.015 | 0.025 | 0.04 | 50 | 50
4 | [5 empty] | FALSE | FALSE | FALSE
5 | [5 empty] | FALSE | FALSE | FALSE
6 | [5 empty] | FALSE | FALSE | FALSE
7 | [5 empty] | FALSE | FALSE | FALSE
8 | [5 empty] | FALSE | FALSE | FALSE | [15 empty] | FALSE
9 | [5 empty] | FALSE | FALSE | FALSE
10 | [5 empty] | FALSE | FALSE | FALSE
3 | 100 | [6 empty] | 10
client |  | negotiated | Lump sum |  |  |  |  | client
a | [7 empty] | client
b | [7 empty] | cp1
client
client
cp2
cp1
fp1
cp3
lp
Specification Complete

## Schedule
Project Schedule
[5 empty] | Precedent Activity 1 | [12 empty] | Precedent Activity 2
|  |  | Activity Duration |  |  |  | START-START |  |  | FINISH-START |  |  | START-FINISH |  |  | FINISH-FINISH |  |  |  | START-START |  |  | FINISH-START |  |  | START-FINISH |  |  | FINISH-FINISH
Activity No. | Activity Name | minimum | most likely | maximum | Activity No. | P | w | d | P | w | d | P | w | d | P | w | d | Activity No. | P | w | d | P | w | d | P | w | d | P | w | d
0 | START |  | 0
1.1 | h |  | 0 | 0
2.1 | tender |  | 0 | 0
2.2 | tender |  | 0 | 0
2.3 | ga |  | 0 | 0
Calculate

## IntRes
70.3577
|  | 120.1537 | 70.3787
|  |  |  | 129.7291 | 70.3931
[6 empty] | 124.0489 | 70.3458
[8 empty] | 128.9531 | 70.4855
118.1175
2

## pmech
[5 empty] | 0.64481 | 0.5 | 0.66318
0.52374 | 49 | 0 | 0.664 | 549 | 0.7399 | 0.87988
0.57123 | 132 | 0 |  |  | 0.69873
0.61871 | 262 | 0 |  |  | 0.86776
0.6662 | 214 | 0 |  |  | 0.62267
0.71368 | 174 | 0 |  |  | 0.56462
0.76117 | 99 | 0 |  |  | 0.59206
0.80865 | 46 | 0 |  |  | 0.64819
0.85614 | 23 | 0 |  |  | 0.79223
0.90362 | 1 | 0 |  |  | 0.61181
0.63626
0.60515
0.67911
0.65463
0.83375
0.557
0.6487
0.75133
0.72398
0.51351
0.64219
Work package 3 |  |  |  |  | 0.5904
Base cost = 0.5 |  |  |  |  | 0.51351
0.68882
0.70195
0.62462
0.58941
0.63404
0.62021
0.86044
0.63166
0.67995
0.67809
0.73218
0.68882
0.51741
0.75133
0.68919
0.67608
0.87512
0.58386
0.82488
0.69391
0.8544
0.7341
0.81445
0.65045
0.60285
0.59318
0.58422
0.69391
0.64748
0.83775
0.62738
0.72508
0.75267
0.73648
0.68919
0.54177
0.71729
0.60743
0.69912
0.73008
0.75435
0.53641
0.61179
0.72288
0.60881
0.58277
0.65134
0.76857
0.76583
0.62355
0.53556
0.5877
0.73125
0.62855
0.64091
0.73916
0.69296
0.63919
0.71474
0.63649
0.63155
0.67443
0.82632
0.68813
0.59057
0.65521
0.52847
0.60657
0.73239
0.68599
0.58206
0.62059
0.69817
0.65281
0.62159
0.5702
0.77306
0.58314
0.68599
0.57063
0.61112
0.68531
0.63866
0.60283
0.61472
0.60342
0.64992
0.66777
0.62281
0.63692
0.72848
0.66824
0.73502
0.70334
0.63866
0.75028
0.67294
0.58838
0.7278
0.62971
0.75865
0.6498
0.61731
0.7424
0.58598
0.7041
0.69007
0.77064
0.81501
0.81882
0.60529
0.56107
0.61524
0.7037
0.57908
0.69225
0.55085
0.74013
0.61394
0.77559
0.74997
0.85211
0.8531
0.65763
0.54177
0.6989
0.75519
0.57792
0.77767
0.63391
0.70506
0.60976
0.5988
0.83215
0.79671
0.72533
0.73077
0.73149
0.6607
0.76663
0.6426
0.695
0.75925
0.63269
0.83375
0.66024
0.76432
0.74446
0.74041
0.82989
0.7362
0.61392
0.56056
0.56346
0.53151
0.74603
0.80857
0.65193
0.5442
0.73599
0.74811
0.63041
0.61179
0.57518
0.63932
0.58772
0.64543
0.64647
0.65704
0.70967
0.62831
0.61603
0.68184
0.67744
0.61457
0.59399
0.72379
0.61742
0.66177
0.65948
0.63017
0.70101
0.74193
0.67377
0.62209
0.77511
0.55828
0.63472
0.57598
0.65612
0.63459
0.62784
0.63975
0.72757
0.69317
0.69027
0.70312
0.55676
0.6311
0.64769
0.60601
0.80909
0.53342
0.74291
0.61193
0.78472
0.72049
0.71126
0.56714
0.62008
0.78431
0.64049
0.74732
0.511
0.62714
0.54907
0.67724
0.79983
0.70925
0.55228
0.69519
0.59972
0.68721
0.70647
0.57354
0.57063
0.77729
0.77349
0.67559
0.61029
0.60049
0.67826
0.7041
0.58975
0.64428
0.62926
0.6222
0.66936
0.72136
0.59559
0.58703
0.65673
0.69703
0.65779
0.53108
0.71729
0.5904
0.7043
0.87709
0.70488
0.79776
0.6233
0.67623
0.65445
0.83775
0.69136
0.63824
0.5442
0.60283
0.59714
0.56488
0.82213
0.64584
0.59634
0.82922
0.69591
0.7194
0.52847
0.84589
0.57674
0.59866
0.7947
0.65581
0.63505
0.61869
0.71292
0.62607
0.62207
0.66777
0.73796
0.71498
0.61233
0.62982
0.62451
0.76088
0.65581
0.54588
0.74142
0.75161
0.63449
0.61392
0.58094
0.64167
0.59573
0.65104
0.6488
0.66318
0.71811
0.63812
0.6207
0.68635
0.68149
0.61757
0.59745
0.72669
0.61945
0.66839
0.66413
0.63348
0.7037
0.74835
0.68706
0.62524
0.7816
0.56205
0.63802
0.58019
0.66255
0.63703
0.6311
0.64377
0.73035
0.69687
0.6928
0.70745
0.55904
0.63745
0.64931
0.61127
0.82551
0.5439
0.74973
0.61326
0.78987
0.72421
0.71965
0.57191
0.62595
0.79179
0.64707
0.7575
0.52202
0.63087
0.65045
0.68373
0.82077
0.70625
0.55956
0.70943
0.60227
0.69099
0.72004
0.57809
0.57908
0.78933
0.78608
0.56205
0.61653
0.60585
0.68742
0.7125
0.58772
0.64718
0.63758
0.62145
0.67709
0.72643
0.6012
0.5914
0.6657
0.71066
0.66332
0.53803
0.72313
0.59495
0.70528
0.68425
0.71582
0.84226
0.62912
0.68288
0.66272
0.85926
0.69798
0.64146
0.55261
0.60686
0.59989
0.56849
0.82922
0.64647
0.59821
0.84308
0.69759
0.72155
0.52799
0.83873
0.57714
0.61341
0.80188
0.65687
0.63569
0.61934
0.7125
0.62653
0.62084
0.67034
0.74142
0.50209
0.6126
0.63027
0.62596
0.76278
0.65779
0.55645
0.78751
0.75243
0.63391
0.61457
0.58111
0.64272
0.59897
0.65117
0.64656
0.66195
0.71921
0.63984
0.62145
0.68849
0.6832
0.6159
0.61099
0.72895
0.6201
0.66936
0.66602
0.6506
0.70822
0.6483
0.58787
0.64387
0.64605
0.56936
0.75577
0.69007
0.66083
0.56804
0.66522
0.76903
0.74997
0.58494
0.71456
0.6227
0.60529
0.75979
0.58668
0.63692
0.69817
0.64667
0.75267
0.53342
0.67358
0.62341
0.61858
0.57167
0.65224
0.68253
0.67034
0.77101
0.54746
0.63224
0.78251
0.6067
0.7133
0.71921
0.50561
0.59304
0.52575
0.61045
0.60049
0.57293
0.59728
0.65855
0.68014
0.58494
0.55482
0.7455
0.67195
0.73239
0.6021
0.67115
0.56601
0.55202
0.59651
0.73383
0.69519
0.69574
0.59805
0.84589
0.69462
0.52907
0.72848
0.75717
0.72155
0.72623
0.61245
0.66698
0.56298
0.70121
0.5851
0.72869
0.69612
0.65207
0.79671
0.72288
0.76201
0.71004
0.68269
0.53151
0.72379
0.63997
0.64367
0.60572
0.79369
0.59381
0.62008
0.64315
0.54718
0.53594
0.58683
0.62415
0.65341
0.77473
0.71664
0.66857
0.52263
0.64554
0.67343
0.63526
0.80298
0.62134
0.62667
0.69725
0.67642
0.55024
0.63909
0.66445
0.63269
0.8646
0.66921
0.58491
0.70625
0.71269
0.60355
0.67458
0.76235
0.65824
0.60459
0.75468
0.60881
0.60686
0.70178
0.57148
0.65372
0.74574
0.59477
0.61808
0.695
0.81082
0.54934
0.66427
0.71707
0.71126
0.62842
0.67082
0.81571
0.64367
0.72643
0.56581
0.60825
0.60047
0.67097
0.7541
0.61615
0.68653
0.63582
0.69207
0.63211
0.61665
0.57714
0.68098
0.7541
0.68531
0.71582
0.5851
0.62725
0.74865
0.65281
0.67097
0.60809
0.57925
0.57477
0.78703
0.60137
0.62402
0.61245
0.58402
0.64146
0.67017
0.72049
0.6182
0.56078
0.64103
0.59302
0.5
0.56462
0.61099
0.74318
0.7947
0.67277
0.53838
0.71145
0.6222
0.66101
0.75892
0.63381
0.67623
0.74651
0.64038
0.78472
0.62784
0.60442
0.61551
0.73527
0.54782
0.60372
0.59463
0.62207
0.6491
0.67277
0.61314
0.8479
0.72488
0.76467
0.71792
0.68567
0.53382
0.74318
0.64251
0.64481
0.60893
0.79717
0.59805
0.62402
0.6444
0.55956
0.5403
0.58956
0.63336
0.65595
0.782
0.72071
0.67995
0.53953
0.64819
0.67892
0.63919
0.8063
0.62595
0.62842
0.70217
0.68373
0.55399
0.51741
0.67195
0.63526
0.66255
0.67477
0.58562
0.71168
0.71707
0.60741
0.67809
0.76704
0.66413
0.50561
0.75979
0.60976
0.60964
0.71045
0.57477
0.6593
0.77222
0.59807
0.6207
0.70005
0.81824
0.55538
0.67214
0.72313
0.71811
0.63802
0.68045
0.61017
0.6444
0.73361
0.57615
0.61472
0.6043
0.68355
0.74164
0.61883
0.69116
0.63975
0.70062
0.63636
0.62738
0.58132
0.68937
0.75691
0.68829
0.72757
0.58873
0.63155
0.75519
0.65838
0.67877
0.61406
0.58386
0.57981
0.80567
0.60755
0.63027
0.6196
0.5877
0.64919
0.67979
0.72353
0.62534
0.55374
0.64315
0.59239
0.87988
0.56669
0.59057
0.74705
0.5329
0.67443
0.5421
0.71292
0.62256
0.66272
0.76049
0.63515
0.67826
0.74705
0.63984
0.78987
0.62902
0.60741
0.61679
0.73746
0.55645
0.60516
0.59557
0.62404
0.64971
0.67181
0.62475
0.56956
0.72533
0.76432
0.71835
0.8531
0.53803
0.74417
0.64336
0.64757
0.60893
0.80517
0.59989
0.62796
0.64491
0.56056
0.54588
0.5962
0.63459
0.66008
0.7889
0.72711
0.65372
0.63292
0.58222
0.6043
0.56823
0.87709
0.75299
0.65297
0.61615
0.68441
0.51909
0.55669
0.68164
0.57495
0.8479
0.59958
0.59042
0.70684
0.73453
0.52453
0.59463
0.53108
0.59366
0.60197
0.82989
0.71394
0.71601
0.61445
0.66163
0.6808
0.77064
0.60909
0.73502
0.6917
0.8003
0.63812
0.69116
0.62642
0.61193
0.64718
0.80517
0.65536
0.58203
0.73266
0.69988
0.60964
0.6989
0.66584
0.64491
0.72895
0.69099
0.63279
0.60962
0.65595
0.75577
0.68547
0.66954
0.77984
0.73361
0.69428
0.72421
0.6356
0.63097
0.65355
0.70121
0.54934
0.6668
0.65687
0.81203
0.70804
0.632
0.75077
0.67979
0.68269
0.70488
0.72353
0.62021
0.63336
0.65917
0.68461
0.66666
0.60062
0.60962
0.7278
0.68014
0.56441
0.75865
0.73768
0.64208
0.61536
0.61601
0.70845
0.56804
0.70027
0.58314
0.62596
0.61945
0.72987
0.62267
0.51817
0.66584
0.66163
0.72268
0.70724
0.5329
0.73841
0.79223
0.57831
0.73891
0.64155
0.60107
0.58019
0.67541
0.6635
0.55804
0.61807
0.75606
0.64324
0.70745
0.69207
0.57396
0.6182
0.69407
0.67458
0.64167
0.76821
0.64081
0.66177
0.70607
0.80298
0.56346
0.63736
0.68441
0.70684
0.56226
0.71372
0.5922
0.58206
0.61112
0.65704
0.63877
0.60797
0.66666
0.62855
0.70295
0.67017
0.6899
0.61017
0.57274
0.64919
0.54521
0.71625
0.77895
0.6676
0.78029
0.6481
0.68813
0.70822
0.6593
0.74394
0.80909
0.59381
0.64503
0.76857
0.59477
0.66506
0.58683
0.73891
0.65432
0.5439
0.70295
0.78431
0.74835
0.72508
0.73916
0.63211
0.7218
0.69798
0.64419
0.5425
0.59106
0.837
0.63877
0.60299
0.62548
0.64594
0.72488

## 3Calc
Project Schedule Calculation Sheet
|  | Simulation Number | 1000 |  | Precedent Activity 1 | [12 empty] | Precedent Activity 2
|  |  | Activity Duration |  |  |  | START-START |  |  | FINISH-START |  |  | START-FINISH |  |  | FINISH-FINISH |  |  |  | START-START |  |  | FINISH-START |  |  | START-FINISH |  |  | FINISH-FINISH
Activity No. | Activity Name | minimum | most likely | maximum | Activity No. | P | w | d | P | w | d | P | w | d | P | w | d | Activity No. | P | w | d | P | w | d | P | w | d | P | w | d
0 | START |  | 0

## Dialogorg
Organisational Structure Label
OK
Give brief description of the contract strategy's organisational structure

## Dialog1
Specify type of tender process
OK
Cancel
WORK PACKAGE
2
one-stage
two-stage
Number of tender activities
competitive
negotiated
Description of tender process
Other:-

## Dialog2
Specify type of pricing mechanism
OK
Cancel
Lump sum
Target cost (with GMP)
Target cost (without GMP)
Cost plus fixed fee
Cost plus % fee
WORK PACKAGE
2

## Dialog3
Lump Sum Pricing Mechansim
OK
Cancel
£
£
£
M
M
M
Minimum Bid
Most Likely Bid
Maximum Bid
Lump Sum Bid

## Dialog4
Target cost (with GMP)
OK
Cancel
Sharing Ratio on any cost savings
Client : Contracting party
:
£
£
£
M
M
M
Minimum target cost
Most Likely target cost
Maximum target cost
Target cost
Minimum fee
Most Likely fee
Maximum fee
Target fee
%
Minimum GMP
Most Likely GMP
Maximum GMP
Guaranteed Maximum Price
%
%
£
£
£
M
M
M

## Dialog5
Target Cost Pricing Mechanism
OK
Cancel
Sharing Ratio on any cost savings
Client : Contractor
:
£
£
£
M
M
M
Minimum target cost
Most Likely target cost
Maximum target cost
Target cost
Minimum fee
Most Likely fee
Maximum fee
Target fee
£
£
£
M
M
M

## Dialog6
Cost plus fixed fee pricing mechanism
OK
Cancel
£
£
£
M
M
M
Minimum Bid
Most Likely Bid
Maximum Bid
Fixed Fee Bid

## Dialog7
Cost plus percentage fee
OK
Cancel
%
%
%
Minimum % fee
Most Likely % fee
Maximum % fee
Perecentage Fee Bid

## Dialog8
Timing of client's payments
OK
Cancel
Work package1
Work package2
Work package3
up-front payment
TIME-RELATED
ACTIVITY-RELATED
interval
Discount rate
%

## Dialog9
Simulation Number
OK
Cancel
100
500
1000
Specify number of simulations

## Dialog10
Default File Path
OK
Cancel
Specify the file path of data files and 'Results' worksheet

## Dialog11
Management/Consultant Fee
OK
Specify type of fee
Lump Sum
Percentage of work package costs
Target fee

## Dialogf1
Lump sum management/consultant fee
OK
Specify lump sum fee
minimum
maximum
most likely

## Dialogf2
Percentage management/consultant fee
OK
Specify fee as a percentage of the work package costs
minimum
maximum
most likely
%
%
%

## Dialogf3
Target management/consultant fee
OK
Fee scale parameter
£
£
£
M
M
M
Minimum target cost
Most Likely target cost
Maximum target cost
Target cost
%
Minimum % fee
Most Likely % fee
Maximum % fee
Perentage fee
%
%
Specify a percentage of the difference between
the target cost and the actual work package cost
which supplements the 'fixed percentage fee'
%

## Dialog12
Cash Flow Analysis
OK
Do you wish to perform cash flow analysis?

## Sheet3
7.2618
0.2 | -0.010256 | 0.19843 | -0.010077
| 0.77551 |  | 0.74454
| 7.8547 |  | 6.5274
| 8.6199 |  | 7.2618

## Dialog13
Dialog Caption
OK
Cancel
Annual net revenue
Number of years over which revenue is received

## wptemp
Definition of work packages
Work package
Activity number | Activity name | General or Specific activity risk | General activity risk owner | Specific actvity risk name | Specific activity risk owner | Specific actvity risk name | Specific activity risk owner | Specific actvity risk name | Specific activity risk owner | Specific actvity risk name | Specific activity risk owner
Specification of all work packages complete

## Qtemp
Work package number:
Activity Number: |  | Activity Name:
Risk Number: |  | Risk Name:
Risk owner:
Activity base cost =
Activity base duration =
Quarterly risk level | most likely | Additional cost | Delay
Negligible (0%) |  | 0 | 0
Marginal (25%)
Serious (50%)
Severe (75%)
Critical (100%)
Specification of all work packages complete

## RDtemp
Specification of Risk Dependencies
Activity Name | Risk Name | Risk no.
Dependency specification complete